FIND MY BAY

UAE Car Wash Aggregator & Smart Booking Platform

Project Plan

Prepared for: Rimas

Version 1.0  ·  April 2026

Companion to: Find My Bay — Architecture & Implementation Plan v1.0

# 1. Executive Summary

This Project Plan is the execution blueprint for Find My Bay — a UAE-focused mobile and web platform that aggregates independent and chain car washes into a single discovery, booking, and smart-departure experience. It complements the Architecture & Implementation Plan v1.0 by translating the technical blueprint into a concrete schedule, work breakdown, ownership model, governance routine, and risk register.

The plan covers a 28-week program from project kickoff through V1.5, structured as four delivery waves: MVP (Dubai pilot), Beta (UAE-3-emirate expansion), V1.0 GA (UAE-wide), and V1.5 (iOS, multi-branch, packages). Today (28 Apr 2026) sits at the end of Foundations Week 1, with backend skeleton, Postgres+PostGIS, auth, vendor discovery, booking, alerts, devices, and realtime modules already scaffolded, plus the Android customer flow (auth, nearby, booking, my bookings, ratings, leave-now) wired end-to-end against the API.

The headline differentiator — the Smart Travel-Time Alert Engine — is on the critical path and is a Beta-phase deliverable. Every other workstream is sized so it does not block, or is blocked by, alert engine validation.

## 1.1 Plan At a Glance

| Wave | Window | Goal | Exit Criteria |
| --- | --- | --- | --- |
| MVP | Wk 1–8 28 Apr → 22 Jun 2026 | Closed pilot, 3–5 vendors in Business Bay / JLT | ≥50 paid bookings, P95 booking API < 400 ms, no Sev-1 in 7 days |
| Beta | Wk 9–14 23 Jun → 3 Aug 2026 | Smart-alert v1, ratings, Arabic, 25 vendors, 1k MAU | Alert accuracy ±5 min ≥ 80%, NPS ≥ 30, vendor self-service ≥ 75% |
| V1.0 GA | Wk 15–20 4 Aug → 14 Sep 2026 | UAE-wide launch, 100 vendors, 10k MAU, loyalty + WhatsApp | App Store rating ≥ 4.3, completion rate ≥ 85%, gross margin positive on infra |
| V1.5 | Wk 21–28 15 Sep → 9 Nov 2026 | iOS, multi-branch vendors, subscriptions, surge pricing | iOS feature parity, ≥3 multi-branch vendors live, sub conversion ≥ 8% |

Total program budget: AED 220k MVP + ~AED 12k/mo run-rate infra, scaling with adoption. See §10 for the financial breakdown.

# 2. Project Scope

## 2.1 In Scope (V1.0 GA)

- Android customer app (Kotlin + Jetpack Compose) — phone OTP auth, nearby map/list, vendor detail, slot booking, payment, smart departure alert, my bookings, ratings, QR check-in.

- Vendor web admin (React + Vite) — brand setup, services & pricing, live bay board with realtime toggling, walk-in entry, bookings pipeline, staff scheduling, owner analytics, payouts.

- Platform admin web — vendor approval, suspensions, audit trail, dispute handling, system health.

- Backend API & realtime gateway — Node.js 20 + Express + Socket.io, PostgreSQL 16 + PostGIS, Redis + BullMQ workers, Prisma ORM.

- Smart Travel-Time Alert Engine — Distance Matrix probe scheduler, push (FCM) + in-app + SMS fallback delivery.

- Payments — Network International primary, Telr secondary, Apple/Google Pay, AED tokenized billing, automated vendor payout reports.

- Compliance — UAE PDPL data-export & deletion endpoints, VAT 5% receipts, TDRA-compliant SMS sender ID, data residency in AWS me-central-1.

- Localization — English + Arabic with full RTL mirroring on Android and Web.

- Observability — OpenTelemetry traces to Grafana Cloud, Sentry crash + error reporting, booking-funnel dashboards, alert-accuracy dashboard.

## 2.2 Out of Scope (deferred / V2+)

- iOS app — moved to V1.5 (week 21+). Android-first decision is final for V1.0.

- At-home or mobile-wash service line — separate product, not part of this program.

- Insurance and damage-claim workflow — vendor's existing policies apply; no platform mediation in V1.

- Full marketplace economics (auctions, real-time surge, dynamic competitive pricing) — early version of off-peak discount lands in V1.5; full marketplace is V2.

- Fleet / B2B contracts — corporate accounts and bulk billing are V2.

## 2.3 Assumptions

- Anthropic-side product owner (Rimas) is available ≥ 8 hours/week for sign-offs and pilot vendor liaison.

- 3 pilot vendors will be signed by end of Wk 4 to enable real-data MVP testing in Wk 6–8.

- Network International merchant onboarding completes within 4 weeks (industry standard for UAE SMEs).

- AWS me-central-1 quota requests for RDS PostgreSQL 16 with PostGIS extension are approved by Wk 2.

- UAE Mainland trade license for the Find My Bay legal entity is already issued at kickoff (a hard prerequisite for payment processing).

## 2.4 Constraints

- Data residency: customer and vendor PII must remain inside the UAE-region AWS account or G42 cloud; no cross-region replicas to EU/US.

- Smart-alert SMS budget capped at AED 4,000/month at MVP traffic levels — drives the OTP rate-limit and WhatsApp migration plan.

- Distance Matrix call budget capped at 12 calls per booking and AED 0.07 per booking in Maps spend.

- App Store / Play Store policies on background location require an active booking; no always-on tracking.

- Ramadan 2027 (mid-Feb to mid-Mar) overlaps with V2 planning; vendor onboarding may slow during this window.

# 3. Objectives & Success Metrics

The program is judged against five strategic goals (carried forward from the Architecture doc), each tied to an instrumented metric, a launch-window target, and the team accountable for it.

| Goal | Metric | MVP Target | GA Target | Owner |
| --- | --- | --- | --- | --- |
| Vendor coverage | Active vendors with ≥1 published bay | 5 | 100+ | BD |
| Customer adoption | Monthly active users | 200 | 10,000 | Growth |
| Booking integrity | Completed / Confirmed bookings | ≥ 75% | ≥ 85% | Product |
| Smart-alert accuracy | Arrival within ±5 min of slot | ≥ 70% | ≥ 90% | Eng |
| Vendor self-service | Vendor changes without support | ≥ 60% | ≥ 90% | Product |
| Reliability | API P95 latency / monthly uptime | < 400 ms / 99.5% | < 250 ms / 99.9% | Eng |
| Unit economics | Gross margin per booking | Break-even | ≥ 35% | Finance |

# 4. Stakeholders, Team & RACI

## 4.1 Stakeholder Map

| Stakeholder | Role | Interest | Engagement |
| --- | --- | --- | --- |
| Rimas | Product Owner / Sponsor | Vision, sign-off, vendor relationships | Weekly steering, daily Slack |
| Pilot vendors (3–5) | Design partners | Bay utilization uplift, booking revenue | Bi-weekly feedback session, in-product NPS |
| Customers (closed pilot) | End users | Reliable booking, accurate ETA | In-app feedback, NPS pulse |
| Network International | Payment processor | Compliance, PCI scope, settlement | Onboarding lead bi-weekly |
| TDRA / PDPL DPO | Regulators / advisor | Compliance posture | Pre-launch review at GA gate |
| AWS / Google Maps | Platform vendors | Quota, billing, support | Account manager monthly check-in |

## 4.2 Core Team

| Role | FTE | Primary Responsibility |
| --- | --- | --- |
| Tech Lead / Backend Eng | 1.0 | Backend, realtime, alert engine, infra, security review, on-call rotation owner |
| Android Engineer | 1.0 | Compose app, FCM, Maps SDK, foreground location, offline resilience |
| Frontend Engineer (Web) | 1.0 | Vendor & admin web, bay board realtime UX, Arabic RTL |
| Backend Engineer #2 | 1.0 | Booking, payments, vendor APIs, Prisma migrations, BullMQ workers |
| Product Designer | 1.0 | End-to-end UX, design system, Arabic RTL, vendor onboarding flow |
| Product Manager (0.5) | 0.5 | Roadmap, vendor pilot, success metrics, customer research |
| QA / Release Engineer (Wk 6+) | 0.5 | Test plans, automation, release management, Play Store submissions |
| BD / Vendor Success (Wk 3+) | 0.5 | Pilot vendor signups, onboarding sessions, training, expansion |

## 4.3 RACI Highlights

R = Responsible · A = Accountable · C = Consulted · I = Informed

| Workstream | Sponsor | PM | TechLead | Android | Web/FE | Designer |
| --- | --- | --- | --- | --- | --- | --- |
| Architecture sign-off | A | C | R | C | C | C |
| Sprint planning | I | A | R | R | R | R |
| Vendor onboarding script | C | A | I | I | C | R |
| Smart-alert engine | I | C | A/R | C | I | I |
| Payments integration | C | C | A/R | C | C | I |
| Arabic RTL rollout | I | C | C | R | R | A |
| Compliance & PDPL review | A | R | C | I | I | I |
| Go/No-Go release gates | A | R | C | C | C | C |

# 5. Work Breakdown Structure

The program decomposes into eight workstreams that run in parallel with explicit dependencies, plus a cross-cutting governance track. Each workstream is sized so its critical-path slice fits within the wave window.

## 5.1 WS-1 · Backend & Infrastructure

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Express + Socket.io skeleton, JWT auth, Prisma + Postgres + PostGIS | MVP | /auth/otp, /vendors/nearby, /bookings happy path, advisory locks for slot booking | Done |
| Bookings, alerts, devices, vendor-members, reviews migrations | MVP | Six migrations applied; PostGIS geog indexes in place | Done |
| BullMQ alert worker + Distance Matrix client + cache layer | Beta | 12-call cap, 3-min cache key (origin grid 250m, dest, hour) | In progress |
| Network International + Telr payment adapters | MVP→Beta | MI primary by Wk 7; Telr fallback by Wk 12 | Pending MI sandbox keys |
| FCM topic + token push, SMS gateway (Unifonic) | MVP | Sender ID 'FINDMYBAY' must be pre-approved; pre-register Wk 2 | In progress |
| BullMQ workers for reminders, no-show sweeper, vendor payout cycle | Beta | Daily cron at 02:00 GST for payout lines | Planned |
| OpenTelemetry → Grafana Cloud, Sentry, alert-accuracy dashboard | Beta | Dashboards: booking funnel, alert ETA error histogram, vendor health | Planned |
| Production AWS me-central-1 setup (RDS PITR, ECS Fargate, Redis, S3, CloudFront) | MVP→GA | Terraform; staging mirrors prod 1:4 sizing | Planned |

## 5.2 WS-2 · Android Customer App

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Auth (PhoneOTP, Verify), Token storage, NetworkModule (Hilt) | MVP | Token rotation, refresh on 401 | Done |
| NearbyMapScreen / NearbyListScreen with Maps SDK + FusedLocation | MVP | Permission rationale card, approximate-location fallback | Done |
| Vendor detail, SlotPicker, BookingConfirmed, ShowQR, MyBookings, RateBooking | MVP | Realtime updates via Socket.io client wrapper | Done |
| LeaveNow alert screen + foreground service for live ETA | Beta | Foreground service starts T-90, kills at ALERTED | In progress |
| FCM service + Doze-mode / OEM autostart rationale flow | MVP→Beta | Xiaomi/Oppo whitelist guidance card | In progress |
| Arabic RTL pass + locale switcher | Beta | Compose Locale.AR, ContentDescription audit | Planned |
| Play Store internal → closed → production track | MVP→GA | Internal at Wk 5, closed beta at Wk 9, prod at Wk 17 | Planned |

## 5.3 WS-3 · Vendor & Admin Web

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| React + Vite scaffold, OTP login, RBAC routing | MVP | TanStack Query, shadcn/ui, Zustand for live state | Planned |
| Brand & branch profile, services & pricing CRUD | MVP | VAT-inclusive flag per service; bay eligibility map | Planned |
| Live Bay Board (drag-toggle status, walk-in entry, current booking on bay) | MVP | Single most demoable surface — prioritize for vendor onboarding sessions | Planned |
| Bookings pipeline (upcoming / in-progress / completed / refunds) | Beta | Refund window: ≥30 min pre-slot full, otherwise minus AED 10 | Planned |
| Staff scheduling, weekly templates, day overrides | Beta | Drag-and-drop weekly grid | Planned |
| Vendor analytics (utilization, no-show, ticket size) | Beta→GA | Charts via Recharts; CSV export | Planned |
| Platform admin (vendor approval, audit log, disputes) | MVP | Used by ops to onboard pilot vendors | Planned |

## 5.4 WS-4 · Smart Alert Engine

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Tick-cadence scheduler (90→1 min) and BullMQ retry strategy | Beta | Each tick re-reads last customer location; idempotent fires | In progress |
| Distance Matrix client with departure_time + traffic_model best_guess | Beta | Cache key (origin 250m grid, dest, HH); 3-min TTL | In progress |
| Geofence suppression (≤200m) + arrival reconciliation | Beta | Drives bay status auto-set on confirmation | Planned |
| Multi-channel delivery (FCM data-only, in-app full-screen, SMS fallback) | Beta | 60s ack timeout before SMS escalation | Planned |
| Alert-accuracy dashboard (ETA error histogram, channel mix, fail reasons) | Beta→GA | SLO: 90% within ±5 min by GA; alerted-on-time funnel | Planned |
| Cost-control guardrails (call-cap per booking, weekly Maps spend alarm) | Beta | PagerDuty if ≥150% of forecast for 2 consecutive days | Planned |

## 5.5 WS-5 · Payments & Money

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Network International merchant + sandbox onboarding | MVP | 4-week typical lead; start Wk 1 | In progress |
| Payment intent / capture / webhook + booking state transitions | MVP | Transition PENDING_PAYMENT → CONFIRMED on capture only | Planned |
| Apple Pay / Google Pay sheet on Android | MVP | Reduces cart abandonment vs raw card form | Planned |
| Refund + cancellation rules engine | Beta | Auto-refund ≥30 min pre-slot; partial otherwise; vendor override | Planned |
| Telr secondary acquirer + automatic failover | Beta→GA | Behind feature flag; kicks in if MI 5xx > 2% over 5 min | Planned |
| Vendor payout reports + settlement to UAE IBAN | GA | Weekly cycle; CSV + PDF; downloadable from analytics | Planned |

## 5.6 WS-6 · Compliance, Security & Privacy

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| PDPL data-export + right-to-deletion endpoints (/me/export, /me/delete) | MVP | PDPL audit blocker if missing — must ship before GA, target MVP | Planned |
| DPO appointment + PIA (Privacy Impact Assessment) | MVP→Beta | External counsel review by Wk 10 | Planned |
| Trade-license verification flow on vendor onboarding | MVP | Manual admin verify; later automate via UAE PASS | Planned |
| VAT 5% on receipts + invoice PDF generator | MVP | vat_inclusive flag drives breakdown rendering | Planned |
| TDRA-compliant SMS sender ID + OTP rate-limit | MVP | 5/hr per number, 5/hr per IP | In progress |
| OWASP ASVS L2 internal pentest + report | Beta | Engaged in Wk 11; remediation within Wk 13 | Planned |
| External pentest | GA | Required before UAE-wide launch announcement | Planned |
| Certificate pinning for api.findmybay.ae in Android | Beta | Backup pin to allow safe rotation | Planned |

## 5.7 WS-7 · Design, Localization & Brand

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Design system v1 (color, type, components) — light + dark, EN + AR | MVP | Figma library; Compose + shadcn parity | In progress |
| Customer onboarding flow (first-run, permissions rationale) | MVP | Card stack with skip; revisit on first booking | In progress |
| Vendor onboarding flow (license upload, branding, first bay) | MVP | Time-to-first-bay target: < 25 min | Planned |
| Arabic RTL audit on Android + Web | Beta | Pseudo-locale stage in CI; native review by AR speaker | Planned |
| Marketing site + App Store / Play Store assets | GA | Hosted on Cloudflare Pages, AR + EN | Planned |
| Brand visual refresh + animated launch reel | GA | Used at UAE-wide launch event | Planned |

## 5.8 WS-8 · Pilot, Growth & Vendor Success

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Recruit 3–5 pilot vendors (Business Bay / JLT) | MVP | Target by end Wk 4; in-person sales-led | Planned |
| Vendor onboarding playbook + training video (EN + AR) | MVP | Used by BD and self-service later | Planned |
| Closed beta customer recruitment (200 users) | MVP | Referral codes, WhatsApp invites | Planned |
| NPS + qualitative interviews after each wave | MVP→GA | 10 customers + 3 vendors per cycle | Planned |
| Public launch event + PR (Khaleej Times / Time Out / Gulf News) | GA | Coordinated with Sponsor and pilot vendors | Planned |
| Loyalty stamp cards + referral program | GA | Drives retention to D90 ≥ 25% | Planned |

## 5.9 WS-9 · Program Governance & QA

| Deliverable | Wave | Notes | Status |
| --- | --- | --- | --- |
| Sprint cadence (1-week sprints) + biweekly steering committee | MVP→V1.5 | Tuesday plan, Friday demo + retro | Active |
| CI: lint, type-check, unit + integration test, Lighthouse a11y | MVP | GitHub Actions; required-checks on main | In progress |
| E2E test suite (Playwright web, Maestro Android) | Beta | Critical paths: book, alert, vendor onboard | Planned |
| Release management runbook + rollback procedures | MVP→GA | DB-migration safety: forward-compatible only; expand-contract | Planned |
| On-call rotation + incident review template | Beta | PagerDuty; 4 engineers in rotation by GA | Planned |
| Weekly status report to Sponsor (RAG + metrics + risks) | MVP→V1.5 | Friday EOD; archived in shared drive | Active |

# 6. Schedule & Milestones

All dates are anchored to a kickoff of Monday 28 April 2026 (today). Sprints are weekly, Tuesday → Monday. Wave gates require an explicit go/no-go with the Sponsor.

## 6.1 Top-line Milestones

| # | Milestone | Target Date | Definition of Done |
| --- | --- | --- | --- |
| M0 | Project Kickoff | 28 Apr 2026 | Charter signed, team staffed, Slack + repo + project board live |
| M1 | Foundations Done | 11 May 2026 | Backend + Android skeletons running locally end-to-end; CI green |
| M2 | First Pilot Vendor Signed | 25 May 2026 | Trade license verified, contract signed, services configured in admin |
| M3 | Internal MVP | 8 Jun 2026 | Full happy-path bookable on Play internal track with seed vendors |
| M4 | MVP Pilot Live (Wave 1 Gate) | 22 Jun 2026 | ≥3 vendors live, ≥50 paid bookings target started, on-call active |
| M5 | Smart Alert Engine v1 | 20 Jul 2026 | Alert ETA error ≤ ±5 min on ≥ 80% of fired alerts in shadow tests |
| M6 | Beta Launch (Wave 2 Gate) | 3 Aug 2026 | Arabic shipped, 25 vendors, 1k MAU; pentest scheduled |
| M7 | Pentest Cleared | 31 Aug 2026 | All highs + criticals remediated; mediums tracked or accepted |
| M8 | V1.0 GA — UAE-wide (Wave 3 Gate) | 14 Sep 2026 | Loyalty + WhatsApp + analytics live; PR + launch event |
| M9 | iOS Internal | 12 Oct 2026 | TestFlight build with feature parity to Android V1.0 |
| M10 | V1.5 Released (Wave 4 Gate) | 9 Nov 2026 | iOS public, multi-branch, subscriptions, off-peak discounts |

## 6.2 Sprint Map (28-week View)

| Sprint | Dates | Focus | Key Deliverables |
| --- | --- | --- | --- |
| S1 | 28 Apr – 4 May | Foundations | Repo hygiene; CI; staging env; Sentry; SMS sender ID submission |
| S2 | 5 – 11 May | Foundations | Vendor admin scaffold; bay-board scaffold; design system v1 |
| S3 | 12 – 18 May | MVP build | Booking happy path on Android against staging; QR flow; payments sandbox |
| S4 | 19 – 25 May | MVP build | Vendor onboarding flow; first pilot vendor signed (M2) |
| S5 | 26 May – 1 Jun | MVP build | Live bay board e2e; admin tools; refund/cancel rules v0 |
| S6 | 2 – 8 Jun | MVP polish | Internal MVP (M3); QA hardening; battery / OEM testing matrix |
| S7 | 9 – 15 Jun | MVP pilot | Closed-pilot release; vendor training; observability dashboards |
| S8 | 16 – 22 Jun | MVP pilot | Pilot bug-fix sprint; Wave-1 gate review (M4) |
| S9–S10 | 23 Jun – 6 Jul | Beta | Smart-alert tick scheduler + Distance Matrix client; cost guardrails |
| S11–S12 | 7 – 20 Jul | Beta | Multi-channel delivery; alert-accuracy dashboard; Arabic RTL phase 1 (M5) |
| S13–S14 | 21 Jul – 3 Aug | Beta launch | Vendor analytics; payout reports; Beta gate (M6) |
| S15–S16 | 4 – 17 Aug | GA push | Pentest + remediation (M7); Telr secondary acquirer; loyalty |
| S17–S18 | 18 – 31 Aug | GA push | WhatsApp template channel; marketing site + assets |
| S19–S20 | 1 – 14 Sep | GA launch | UAE-wide rollout; PR; launch event (M8) |
| S21–S24 | 15 Sep – 12 Oct | V1.5 dev | iOS app build; multi-branch model; subscription billing (M9) |
| S25–S28 | 13 Oct – 9 Nov | V1.5 release | Surge / off-peak pricing; iOS App Store launch (M10) |

## 6.3 Critical Path

The critical path runs through the Smart Alert Engine. Beta (M6) cannot be declared without alert accuracy meeting threshold; GA (M8) cannot be declared without pentest sign-off (M7), which is itself blocked on a stable Beta. Any slip in M5 (Smart Alert v1) cascades to M6 and M8 1:1, so the engine is staffed with the Tech Lead full-time across S9–S12.

Secondary critical paths are payment merchant onboarding (M2 prerequisite for paid bookings) and the Arabic RTL pass (Beta gate). Both have explicit lead-time mitigations in §8.

# 7. Dependencies

| Dependency | On / From | Needed By | Owner |
| --- | --- | --- | --- |
| AWS me-central-1 RDS quota + PostGIS | AWS | Wk 2 (S2) | TechLead |
| Network International merchant + sandbox keys | Network International | Wk 5 (M3 readiness) | PM |
| TDRA-approved SMS sender ID 'FINDMYBAY' | Unifonic / Etisalat | Wk 4 | BackendEng2 |
| Google Maps Platform billing + raised quota | Google | Wk 2 | TechLead |
| Firebase project + APNs key (later for iOS) | Google | Wk 1 / Wk 21 (iOS) | Android |
| 3 pilot vendor contracts + trade licenses | Vendors / BD | Wk 4 (M2) | BD |
| UAE Mainland trade license for Find My Bay entity | Sponsor | Pre-kickoff (already issued) | Sponsor |
| External pentest provider engagement | Pentest vendor | Wk 11 booking, Wk 14 start | TechLead |
| Apple Developer account (paid) | Apple | Wk 21 | Sponsor |
| Network International live keys + go-live approval | Network International | Wk 18 (GA gate) | PM |

# 8. Risk Register

Top program risks with likelihood (L), impact (I), and concrete mitigations. Reviewed every other steering committee.

| Risk | L | I | Mitigation |
| --- | --- | --- | --- |
| FCM throttled on Chinese OEMs (Xiaomi/Oppo) — alerts dropped | H | H | SMS fallback after 60s; foreground service in last 30 min; in-app rationale to whitelist autostart; track delivery success per OEM |
| Distance Matrix cost spike at scale | M | M | 12-call cap per booking; (origin grid 250m, dest, hour) cache; weekly spend alarm; switch visuals to Mapbox tiles if needed |
| Vendors fake bay status to look free | M | H | Auto-set bay busy on booking confirmation; arrival reconciliation; review-weighted ranking; admin spot-checks |
| Customer no-shows hurt vendor utilization | H | M | Pre-auth full price; AED 10 cancellation fee within 30 min; 3-strike auto-block; vendor-managed walk-in slot recovery |
| Network International merchant onboarding delay | M | H | Start Wk 1; Telr engaged as parallel secondary; cash-on-arrival not enabled in V1 to keep pressure on schedule |
| Pilot vendor recruitment slower than 5 by Wk 4 | M | M | BD outreach starts pre-kickoff; offer 0% platform fee for first 90 days; widen catchment to Marina if Business Bay/JLT slips |
| Pentest finds high-severity issue late | L | H | Internal pentest at Wk 11; remediation buffer in Wk 13; external test as gate at M7 with 2-week recovery slack before GA |
| PDPL audit finding (data export missing or partial) | L | H | Ship /me/export and /me/delete in MVP, not deferred; DPO sign-off as part of Wave-1 gate |
| Map permissions denied on Android 14+ | M | H | Approximate-location fallback path; manual address entry; degraded list view that still allows booking |
| Key engineer unavailability (illness, attrition) | L | H | Knowledge handoff doc per workstream; pair-programming on critical-path components; on-call buddy system |
| Ramadan vendor-onboarding slowdown (V2 horizon) | M | L | Pull V2 BD calendar earlier; lean into vendor self-service to reduce live support need during Ramadan window |
| WhatsApp Business API approval slow (V1.0 GA dep) | M | M | Apply Wk 8; SMS retains as primary fallback; WhatsApp gracefully degrades if not approved by GA |

# 9. Communication & Governance

## 9.1 Cadence

| Forum | Frequency | Audience | Purpose |
| --- | --- | --- | --- |
| Daily standup | Mon–Fri, 09:30 GST | Team | 15-min blockers + plan-of-day |
| Sprint planning | Tue, 14:00 | Team + PM | 1-week sprint commitment |
| Sprint review + retro | Fri, 16:00 | Team + Sponsor (review only) | Demo + reflective adjustments |
| Steering committee | Bi-weekly Tue | Sponsor + PM + TechLead | Scope, risks, gate decisions, budget |
| Vendor pilot sync | Bi-weekly Wed | Sponsor + BD + lead pilot vendors | Field feedback, feature priorities |
| Incident review | Within 48h of any Sev-1/2 | Team + on-call + PM | Blameless postmortem + action items |

## 9.2 Reporting

- Weekly status report (Friday EOD) — RAG status per workstream, milestones hit/missed, top 3 risks, key metrics.

- Monthly business review — burn rate vs budget, customer/vendor metrics, runway impact.

- Live program dashboard — Linear board for tasks; Grafana for product KPIs; both linked from the program homepage.

## 9.3 Decision Rights

- Architecture changes that affect another workstream → Tech Lead approves; Sponsor informed.

- Scope additions that affect a wave date → Sponsor + PM joint decision; documented in change log.

- Budget changes >10% of any line item → Sponsor approval.

- Go/No-Go for each wave gate → Sponsor accountable; PM facilitates; TechLead consulted; Designer + Eng heads consulted.

# 10. Budget Summary

Estimates are AED, indicative, and aligned with the cost estimate in the Architecture doc. Variable costs scale with vendor and customer counts; figures below assume the GA target (10k MAU, 5k bookings/mo).

| Line Item | Amount (AED) | Notes |
| --- | --- | --- |
| MVP build (8 weeks · core team) | ~ 220,000 one-off | 2 mobile + 2 backend + 1 design + 0.5 PM at ~AED 27.5k/wk |
| Beta build (6 weeks) | ~ 180,000 one-off | Adds 0.5 QA + 0.5 BD; alert engine emphasis |
| GA push + launch (6 weeks) | ~ 220,000 one-off | Includes pentest, marketing site, launch event |
| V1.5 (8 weeks) | ~ 260,000 one-off | iOS + multi-branch + subscriptions; +1 iOS engineer |
| AWS me-central-1 (steady state) | 3,500 – 5,500 / mo | RDS, ECS Fargate, ElastiCache, S3, CloudFront |
| Google Maps Platform | 1,500 – 3,000 / mo | Heavy on Distance Matrix; aggressive cache |
| SMS via Unifonic (~AED 0.12/OTP) | 3,600 / mo @ MVP | Largest single variable; migrate part to WhatsApp at GA |
| Sentry + Grafana Cloud + misc | 600 / mo | Growth tier |
| External pentest (annual) | ~ 35,000 one-off | Required at GA |
| Total infra (steady state) | 9,200 – 12,700 / mo | Excludes payment processing fees (% of GMV) |

# 11. Acceptance Criteria & Sign-off

Each wave is closed by a written acceptance from the Sponsor against the criteria below.

### MVP (Wave 1) acceptance

- ≥ 3 vendors live with services and pricing configured.

- End-to-end customer flow works on Android internal track: OTP → nearby → vendor → slot → pay (real card via NI sandbox graduating to live) → confirmation → QR → completion → rating.

- Vendor admin web allows brand setup, bay toggling, services CRUD, bookings list.

- Smart alert delivers a manual placeholder push (Distance Matrix integration is Beta).

- PDPL data-export and deletion endpoints live and exercised in QA.

- No Sev-1 issues outstanding for 7 consecutive days; on-call rotation active.

### Beta (Wave 2) acceptance

- Smart-alert engine ETA error ≤ ±5 min on ≥ 80% of fired alerts (rolling 7 days, ≥ 200 alerts).

- Arabic RTL passes audit on all customer flows.

- ≥ 25 vendors active across 3 emirates; ≥ 1,000 monthly active users.

- Internal pentest closed; criticals/highs remediated.

### V1.0 GA (Wave 3) acceptance

- App Store and Play Store production tracks live with rating ≥ 4.3 on initial launch sample.

- Booking completion rate ≥ 85%.

- External pentest cleared.

- Loyalty + WhatsApp alert channel + vendor analytics shipped.

- PR launch executed; ≥ 100 vendors signed.

### V1.5 (Wave 4) acceptance

- iOS feature parity with Android V1.0; TestFlight then App Store launch.

- Multi-branch vendor model live with at least 3 multi-branch vendors.

- Subscription package conversion ≥ 8% of returning customers.

- Off-peak / surge discount engine active; vendor opt-in dashboard available.

# 12. Change Control

Any change request that affects scope, schedule, or budget is logged in the Program Change Log (shared drive). The PM triages; the Sponsor approves changes that move a wave date or add ≥ 5% to the budget. Architecture-affecting changes require Tech Lead written sign-off attached to the change record.

This Plan is a living document. It is reviewed and re-baselined at each wave gate. Version 1.0 (28 Apr 2026) supersedes any prior verbal plan; v1.1 will be issued at the close of MVP with actuals replacing forecasts in §6, §10.

End of document — Find My Bay Project Plan v1.0